## Detailed Gantt Chart
MANTIS Zero-Dependency HIDS ¦ Project Schedule ¦ CI/CT Pipeline ¦ Anuskar Sigdel ¦ Jan-Oct 2026
Breakdown Structure (WBS) | Stage | JANUARY |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER
Breakdown Structure (WBS) | Stage | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38
SPRINT 0 - Domain Investigation & Planning
• Documentation & Project Planning | Sprint 0
• Literature Review & Academic Research | Sprint 0
• Analyze Zero-Day Threats & HIDS Limitations | Sprint 0
• OSI Layer 2 Socket Feasibility Study | Sprint 0
• Sprint 0 Review & Retrospective | Sprint 0
SPRINT 1 - Requirements & Architecture Design
• Define Raw Socket Packet Structs | Sprint 1
• Design Asynchronous Thread Flow | Sprint 1
• Define JSON IPC Schema for SIEM | Sprint 1
• Localhost UDP Bridge Architecture | Sprint 1
• Sprint 1 Documentation & Log Update | Sprint 1
• Sprint 1 Review & Retrospective | Sprint 1
SPRINT 2 - L2 Sensor Construction
• Initialize Raw AF_PACKET Sockets | Sprint 2
• Develop Hexadecimal to ASCII Parser | Sprint 2
• Extract Ethernet & IP Headers | Sprint 2
• Implement Multiprocessing Pipe Routing | Sprint 2
• Optimize Ingestion Zero-Copy Flow | Sprint 2
• Sprint 2 Documentation & Log Update | Sprint 2
• Sprint 2 Review & Retrospective | Sprint 2
SPRINT 3 - Machine Learning Algorithm Engine
• Code Z-Score Volumetric Mathematics | Sprint 3
• Develop KNN Behavioral Clustering | Sprint 3
• Implement Euclidean Distance Logic | Sprint 3
• Code Naive Bayes Text Analysis Array | Sprint 3
• Integrate Engines with Sensor Pipeline | Sprint 3
• Sprint 3 Documentation & Log Update | Sprint 3
• Sprint 3 Review & Retrospective | Sprint 3
SPRINT 4 - SIEM Interface & Active Defense
• Build Lightweight HTTP Web Server | Sprint 4
• Develop HTML/JS Dashboard UI | Sprint 4
• Map JSON Alerts to UI Data Tables | Sprint 4
• Implement iptables Active Blocking Scripts | Sprint 4
• Sprint 4 Documentation & Log Update | Sprint 4
• Sprint 4 Review & Retrospective | Sprint 4
SPRINT 5 - Testing & Evaluation Pipeline
• Execute Nmap Aggressive Port Scans | Sprint 5
• Simulate hping3 Volumetric Floods | Sprint 5
• Inject SQLi/XSS Payloads for Testing | Sprint 5
• Compile True/False Positive Metrics | Sprint 5
• Final Dissertation Report Finalization | Sprint 5
• Project Defense Preparation | Sprint 5