## Detailed Gantt Chart
MANTIS Zero-Dependency HIDS ¦ Project Schedule ¦ CI/CT Pipeline ¦ Anuskar Sigdel ¦ Jan-Oct 2026
Breakdown Structure (WBS) | Stage | DONE |  | NOT DONE |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38
SPRINT 0 - Domain Investigation & Planning
• Documentation & Project Planning | Sprint 0 | bar: DONE W1 to DONE W2
• Literature Review & Academic Research | Sprint 0 | bar: DONE W2 to NOT DONE W3
• Analyze Zero-Day Threats & HIDS Limitations | Sprint 0 | bar: NOT DONE W3 to NOT DONE W4
• OSI Layer 2 Socket Feasibility Study | Sprint 0 | bar: NOT DONE W4
• Sprint 0 Review & Retrospective | Sprint 0 | bar: NOT DONE W4
SPRINT 1 - Requirements & Architecture Design
• Define Raw Socket Packet Structs | Sprint 1 | bar: NOT DONE W5 to NOT DONE W6
• Design Asynchronous Thread Flow | Sprint 1 | bar: NOT DONE W6 to MARCH W8
• Define JSON IPC Schema for SIEM | Sprint 1 | bar: MARCH W7 to MARCH W8
• Localhost UDP Bridge Architecture | Sprint 1 | bar: MARCH W8 to MARCH W10
• Sprint 1 Documentation & Log Update | Sprint 1 | bar: MARCH W9 to MARCH W10
• Sprint 1 Review & Retrospective | Sprint 1 | bar: MARCH W10
SPRINT 2 - L2 Sensor Construction
• Initialize Raw AF_PACKET Sockets | Sprint 2 | bar: MARCH W10 to APRIL W12
• Develop Hexadecimal to ASCII Parser | Sprint 2 | bar: MARCH W11 to APRIL W14
• Extract Ethernet & IP Headers | Sprint 2 | bar: APRIL W13 to APRIL W15
• Implement Multiprocessing Pipe Routing | Sprint 2 | bar: APRIL W14 to MAY W17
Fix GIL Contention with Bounded Queue | Sprint 2 | bar: APRIL W15; MAY W17 to MAY W18
• Sprint 2 Documentation & Log Update | Sprint 2 | bar: MAY W18
• Sprint 2 Review & Retrospective | Sprint 2 | bar: MAY W18 to MAY W19
SPRINT 3 - Machine Learning Algorithm Engine
• Code Z-Score Volumetric Mathematics | Sprint 3 | bar: MAY W19 to JUNE W22
• Develop KNN Behavioral Clustering | Sprint 3 | bar: JUNE W21 to JUNE W24
Implement K-Means Online Clustering | Sprint 3 | bar: JUNE W23 to JULY W25
Code Naive Bayes & Bloom Filter Engines | Sprint 3 | bar: JUNE W24 to JULY W27
• Integrate Engines with Sensor Pipeline | Sprint 3 | bar: JULY W27 to AUGUST W29
• Sprint 3 Documentation & Log Update | Sprint 3 | bar: AUGUST W29 to AUGUST W30
• Sprint 3 Review & Retrospective | Sprint 3 | bar: AUGUST W29 to AUGUST W30
SPRINT 4 - SIEM Interface & Active Defense
• Build Lightweight HTTP Web Server | Sprint 4 | bar: AUGUST W30 to AUGUST W31
• Develop HTML/JS Dashboard UI | Sprint 4 | bar: AUGUST W31 to AUGUST W32
Integrate Forensic HTML Export Feature | Sprint 4 | bar: AUGUST W32 to AUGUST W33
• Implement iptables Active Blocking Scripts | Sprint 4 | bar: AUGUST W33 to SEPTEMBER W34
• Sprint 4 Documentation & Log Update | Sprint 4 | bar: AUGUST W33 to SEPTEMBER W34
• Sprint 4 Review & Retrospective | Sprint 4 | bar: SEPTEMBER W34
SPRINT 5 - Testing & Evaluation Pipeline
Benchmark Memory/CPU vs Snort & Wazuh | Sprint 5 | bar: SEPTEMBER W34 to SEPTEMBER W35
Evaluate Offline vs CIC-IoT2023 Dataset | Sprint 5 | bar: SEPTEMBER W35
• Inject SQLi/XSS Payloads for Testing | Sprint 5 | bar: SEPTEMBER W35 to SEPTEMBER W36
• Compile True/False Positive Metrics | Sprint 5 | bar: SEPTEMBER W36
• Final Dissertation Report Finalization | Sprint 5 | bar: SEPTEMBER W36 to OCTOBER W38
• Project Defense Preparation | Sprint 5 | bar: SEPTEMBER W37